## Risks
Description | Evaluation | Likelihood | Impact level | Responsibility | Response | Control Measure | ID
Github crashes | I lose all my version history and work | Low | High | GitHub | Restart Project | Keep a secondary backup of most recent working project build | 1
Broken final version | Product does not function at launch | Low | High | Me | Return to working version | Have a working MVP by maintaining FBM version control | 2
Merge feature early | new merged code is faulty | Low | Low | Me | Return to working version | Set branch protection to stop automatic merge without review | 3
Real life problem requires attention | Stop coding to sort issue | High | Medium | Me | Sort issue and return to coding when able | Sort life issue after work and make sure no commitments are set during work times | 4
Project MVP requirements change | Previous work is useless | Low | Medium | Customer | Salvage existing code that can be used and replan | Keep updated with the Customer product scope page | 5
Keyboard and Mouse faults | Can't use desktop to code | Medium | Medium | Manufacturer | Go buy new equipment or borrow laptop | Maintain safe peripheral usage | 6
Internet goes down | Can't connect to JIRA or gitHub | Medium | Low | Virgin Media | Use Hotspot from Phone | Ethernet connect into router to avoid wifi drops | 7

## Matrix
LIKELIHOOD | IMPACT LEVEL
| LOW | MEDIUM | HIGH
LOW | 3 | 5 | 1,2
MEDIUM | 7 | 6
HIGH |  | 4